## Projects
Job_Number | Province | Project_Name | Project_Type | Contracted_Budget | Actual_Costs | Committed_Costs | Budget_Used_Pct | Variance_Amount | Variance_Pct | Status | Completion_Pct | Notes
BC-2401 | BC | Northgate Community Centre | Community Facility | 1240000 | 876500 | 142000 | 70.69% | 221500 | 17.86% | In Progress | 74% | Structural phase complete; mechanical underway
AB-2402 | AB | Riverside Office Tower Fitup | Commercial Fitup | 3850000 | 3791200 | 42000 | 98.47% | 16800 | 0.4364% | In Progress | 98% | Deficiency list in progress; handover Q3 2025
ON-2403 | ON | Lakeview Retail Plaza Reno | Retail Renovation | 920000 | 943600 | 0 | 102.6% | -23600 | -2.565% | Completed | 100% | Over budget; change orders approved by owner
NS-2404 | NS | Harbour District Apartments | Multi-Unit Residential | 2680000 | 1608000 | 536000 | 60% | 536000 | 20% | In Progress | 60% | On schedule; envelope work ahead of plan
NB-2405 | NB | Eastside Medical Clinic Fitup | Healthcare Fitup | 580000 | 203000 | 145000 | 35% | 232000 | 40% | In Progress | 35% | Permit delay resolved; back on track

## Monthly_Costs
Project_Name | Month | Budget_Monthly | Actual_Monthly | Variance_Monthly
Northgate Community Centre | Jan-25 | 100000 | 95000 | 5000
Northgate Community Centre | Feb-25 | 120000 | 112000 | 8000
Northgate Community Centre | Mar-25 | 140000 | 134000 | 6000
Northgate Community Centre | Apr-25 | 155000 | 148000 | 7000
Northgate Community Centre | May-25 | 180000 | 175000 | 5000
Northgate Community Centre | Jun-25 | 220000 | 212500 | 7500
Riverside Office Tower Fitup | Jan-25 | 590000 | 580000 | 10000
Riverside Office Tower Fitup | Feb-25 | 620000 | 612000 | 8000
Riverside Office Tower Fitup | Mar-25 | 660000 | 648000 | 12000
Riverside Office Tower Fitup | Apr-25 | 600000 | 591000 | 9000
Riverside Office Tower Fitup | May-25 | 730000 | 720000 | 10000
Riverside Office Tower Fitup | Jun-25 | 650000 | 640200 | 9800
Lakeview Retail Plaza Reno | Jan-25 | 130000 | 145000 | -15000
Lakeview Retail Plaza Reno | Feb-25 | 145000 | 158000 | -13000
Lakeview Retail Plaza Reno | Mar-25 | 150000 | 162000 | -12000
Lakeview Retail Plaza Reno | Apr-25 | 155000 | 171000 | -16000
Lakeview Retail Plaza Reno | May-25 | 145000 | 155000 | -10000
Lakeview Retail Plaza Reno | Jun-25 | 140000 | 152600 | -12600
Harbour District Apartments | Jan-25 | 220000 | 212000 | 8000
Harbour District Apartments | Feb-25 | 260000 | 248000 | 12000
Harbour District Apartments | Mar-25 | 290000 | 287000 | 3000
Harbour District Apartments | Apr-25 | 280000 | 275000 | 5000
Harbour District Apartments | May-25 | 300000 | 298000 | 2000
Harbour District Apartments | Jun-25 | 290000 | 288000 | 2000
Eastside Medical Clinic Fitup | Jan-25 | 20000 | 18000 | 2000
Eastside Medical Clinic Fitup | Feb-25 | 25000 | 22000 | 3000
Eastside Medical Clinic Fitup | Mar-25 | 38000 | 35000 | 3000
Eastside Medical Clinic Fitup | Apr-25 | 52000 | 48000 | 4000
Eastside Medical Clinic Fitup | May-25 | 45000 | 42000 | 3000
Eastside Medical Clinic Fitup | Jun-25 | 40000 | 38000 | 2000