## Project Tracker
CONSTRUCTION PROJECT FINANCIAL TRACKER ¦ Atlantic Build Corp.
Multi-Province Portfolio ¦ FY 2024–2025 ¦ Finance Department ¦ All amounts in CAD
Job # | Province | Project Name | Project Type | Contracted Budget ($) | Actual Costs To Date ($) | Committed Costs ($) | Budget Used (%) | Variance ($) | Variance (%) | Status | Completion (%) | Notes
BC-2401 | BC | Northgate Community Centre | Community Facility | 1240000 | 876500 | 142000 | 70.69% | 221500 | 17.86% | In Progress | 75% | Structural phase complete; mechanical underway
AB-2402 | AB | Riverside Office Tower Fitup | Commercial Fitup | 10850000 | 3791200 | 42000 | 98.47% | 16800 | 0.4364% | In Progress | 98% | Deficiency list in progress; handover Q3
ON-2403 | ON | Lakeview Retail Plaza Reno | Retail Renovation | 920000 | 943600 | 0 | 102.6% | -23600 | -2.565% | Completed | 100% | Over budget; change orders approved by owner
NS-2404 | NS | Harbour District Apartments | Multi-Unit Residential | 2680000 | 1608000 | 536000 | 60% | 536000 | 20% | In Progress | 60% | On schedule; envelope work ahead of plan
NB-2405 | NB | Eastside Medical Clinic Fitup | Healthcare Fitup | 580000 | 203000 | 145000 | 35% | 232000 | 40% | In Progress | 35% | Permit delay resolved; back on track
PORTFOLIO TOTALS |  |  |  | 16270000 | 7422300 | 865000 | 45.62% | 982700 | 6.04% |  | 73.6%
PORTFOLIO SUMMARY
Total Projects | 5 | Active Projects | 4 | Completed | 1 | Portfolio Value ($) | 16270000 | Costs to Date ($) | 7422300 | Budget Remaining ($) | 982700

## Variance Analysis
MONTHLY COST VARIANCE ANALYSIS — FY 2025
Project | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25
Northgate Community Centre | 100000 | 120000 | 140000 | 155000 | 180000 | 220000
| 95000 | 112000 | 134000 | 148000 | 175000 | 212500
| 5000 | 8000 | 6000 | 7000 | 5000 | 7500
Riverside Office Tower Fitup | 590000 | 620000 | 660000 | 600000 | 730000 | 650000
| 580000 | 612000 | 648000 | 591000 | 720000 | 640200
| 10000 | 8000 | 12000 | 9000 | 10000 | 9800
Lakeview Retail Plaza Reno | 130000 | 145000 | 150000 | 155000 | 145000 | 140000
| 145000 | 158000 | 162000 | 171000 | 155000 | 152600
| -15000 | -13000 | -12000 | -16000 | -10000 | -12600
Harbour District Apartments | 220000 | 260000 | 290000 | 280000 | 300000 | 290000
| 212000 | 248000 | 287000 | 275000 | 298000 | 288000
| 8000 | 12000 | 3000 | 5000 | 2000 | 2000
Eastside Medical Clinic Fitup | 20000 | 25000 | 38000 | 52000 | 45000 | 40000
| 18000 | 22000 | 35000 | 48000 | 42000 | 38000
| 2000 | 3000 | 3000 | 4000 | 3000 | 2000

## Budget vs Actual
BUDGET vs ACTUAL vs REMAINING — Project Summary
Project | Contracted Budget ($) | Actual Costs ($) | Budget Remaining ($)
Northgate Community Centre | 1240000 | 876500 | 221500
Riverside Office Tower Fitup | 3850000 | 3791200 | 16800
Lakeview Retail Plaza Reno | 920000 | 943600 | 23600
Harbour District Apartments | 2680000 | 1608000 | 536000
Eastside Medical Clinic Fitup | 580000 | 203000 | 232000

## Notes & Legend
NOTES & COLOR LEGEND
SECTION | DESCRIPTION
Blue text | Hardcoded input assumptions (user-editable)
Black text | Calculated formulas
Green text / fill | Positive variance — under budget / Completed
Red text / fill | Negative variance — over budget / At Risk
Light blue fill | In Progress status or high completion
Amber fill | Completion below 50% — monitor closely
COLUMN DEFINITIONS
Contracted Budget ($) | Approved contract value including all change orders
Actual Costs to Date ($) | Invoiced and posted costs as of report date
Committed Costs ($) | Approved POs / subcontracts not yet invoiced
Budget Used (%) | Actual ÷ Budget — measures cost burn rate
Variance ($) | Budget minus Actual minus Committed
Variance (%) | Variance $ ÷ Budget
Completion (%) | Physical % complete as reported by PM
PROJECT NOTES
Data | All project names and figures are illustrative
Frequency | Report updated monthly by Finance team
Source | Costs imported from accounting system (QuickBooks / Sage 50)
Prepared by | Finance Department — Atlantic Build Corp.