## Project Tracker
CONSTRUCTION PROJECT FINANCIAL TRACKER — Atlantic Build Corp.
Multi-Province Portfolio ¦ FY 2024–2025 ¦ All amounts in CAD
Project_Name | Province | Contracted_Budget | Actual_Costs | Committed_Costs | Variance_Amount | Completion_Pct | Status
Northgate Community Centre | BC | 1240000 | 876500 | 142000 | 221500 | 75% | In Progress
Riverside Office Tower Fitup | AB | 3850000 | 3791200 | 42000 | 16800 | 98% | In Progress
Lakeview Retail Plaza Reno | ON | 920000 | 943600 | 0 | -23600 | 100% | Completed
Harbour District Apartments | NS | 2680000 | 1608000 | 536000 | 536000 | 60% | In Progress
Eastside Medical Clinic Fitup | NB | 580000 | 203000 | 145000 | 232000 | 35% | In Progress
PORTFOLIO TOTALS |  | 9270000 | 7422300 | 865000 | 982700 | 73.6%
PORTFOLIO SUMMARY
Total Projects | 5 | Portfolio Value | 9270000 | Costs to Date | 7422300 | Budget Remaining | 982700 | Avg Completion | 73.6%